## Sheet1
PROJECT SHORE LINE: SCHEDULE
Great Pacific Credit Union
| Documentation Project Leader: Rachelle Gervacio |  | About (click here) |  |  | August (2018) | [30 empty] | September (2018) | [29 empty] | October (2018) | [30 empty] | November (2018) | [29 empty] | December (2018)
| Project Start Date: August 1, 2018 |  | Legend (click here) |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30
| Task(s) | Resource(s) | Start | End | No. Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Task Description | 1) Plan (Aug. 1/18 – Aug. 13/18)
Plan (Aug. 1/18 – Aug. 13/18) | Determine the project’s scope and goals. | Project Manager | 2018-08-01 | 2018-08-02 | 2 | bar: August (2018) 1 to August (2018) 2
Determine the project’s scope and goals. | Estimate the project’s schedule, budget, and resources. | Project Manager | 2018-08-03 | 2018-08-07 | 3 | bar: August (2018) 3 to August (2018) 7
Estimate the project’s schedule, budget, and resources. | Create a document outline and content plan. | Project Manager | 2018-08-08 | 2018-08-10 | 3 | bar: August (2018) 8 to August (2018) 10
Create a document outline and content plan. | Discuss plan with team members and stakeholders. | Project Manager | 2018-08-13 | 2018-08-13 | 1 | bar: August (2018) 11 to August (2018) 13
Discuss plan with team members and stakeholders.
2) Design (Aug. 14/18 – Sept. 7/18)
Design (Aug. 14/18 – Sept. 8/18) | Conduct audience and task analysis. | Content Strategist I, II, III | 2018-08-14 | 2018-08-20 | 5 | bar: August (2018) 14 to August (2018) 20
Conduct audience and task analysis. | Identify information design, usability, and accessibility goals. | Project Manager | 2018-08-14 | 2018-08-20 | 5 | bar: August (2018) 14 to August (2018) 20
Identify information design, usability, and accessibility goals. | Design content for the online, print, and accessible deliverables. | Project Manager | 2018-08-21 | 2018-09-07 | 13 | [37 empty] | M | bar: August (2018) 21 to August (2018) 31
Design content for the online, print, and accessible deliverables. | Online: FAQ guide, user support articles, and video tutorials. | Content Strategist I, II, III | 2018-08-21 | 2018-08-24 | 4
Online: FAQ guide, user support articles, and video tutorials. | Print: Quick-start pamphlet, user guide, and large print guide. | Content Strategist I, II, III | 2018-08-27 | 2018-08-31 | 5 | bar: August (2018) 25 to August (2018) 26
Print: Quick-start pamphlet, user guide, and large print guide. | Accessible: Braille transcription and audio recordings of the user guide. | Content Strategist I, II, III | 2018-09-04 | 2018-09-07 | 4
3) Develop (Sept. 10/18 – Nov. 9/18)
| Monitor project development and assist other team members. | Project Manager | 2018-09-10 | 2018-11-09 | 43
| Evaluate schedule progress, budget, and documentation quality. | Project Manager | 2018-09-14 | 2018-11-09 | 9
| Report progress to upper management and stakeholders. | Project Manager | 2018-09-21 | 2018-11-09 | 5
| Index content | Content Strategist I, II | 2018-11-05 | 2018-11-06 | 2
| Final edit and revision | Proofreader/Editor I, II | 2018-11-07 | 2018-11-09 | 3 | [100 empty] | M
Deliverables
| a) User guide (Print - 25 pgs.) |  | 2018-09-10 | 2018-10-04 | 18.5 | [64 empty] | M
| Write content. | Content Strategist I, II, III | 2018-09-10 | 2018-10-04 | 18.5
| Introduction to Online Banking (6 pgs.) |  | 2018-09-10 | 2018-09-12 | 3
| Personal Banking (5 pgs.) |  | 2018-09-13 | 2018-09-17 | 3
| Personal Loans and Mortgages (4 pgs.) |  | 2018-09-18 | 2018-09-21 | 4
| Investing (5 pgs.) |  | 2018-09-24 | 2018-09-28 | 4.5
| Account Settings, Cheque Orders, and Customer Support (5 pgs.) |  | 2018-10-01 | 2018-10-04 | 4
| Edit content. | Proofreader/Editor I, II | 2018-09-21 | 2018-10-04 | 10
| Test content. | QA Team Member | 2018-10-03 | 2018-10-04 | 2
| b) Large print guide (Print - 30 pgs.) |  | 2018-10-05 | 2018-10-16 | 6.5
| Import user guide content. | Content Strategist I, II | 2018-10-05 | 2018-10-05 | 1
| Format large print text. | Content Strategist I, II | 2018-10-09 | 2018-10-16 | 6
| Edit content. | Proofreader/Editor I | 2018-10-15 | 2018-10-16 | 2
| Test content. | QA Team Member | 2018-10-16 | 2018-10-16 | 1
| c) Quick-start pamphlet (Print - 6 pgs.) |  | 2018-10-18 | 2018-10-23 | 4
| Write content. | Content Strategist I, II | 2018-10-18 | 2018-10-23 | 4
| How to use the online banking service (4 pgs.) |  | 2018-10-18 | 2018-10-19 | 2
| Troubleshoot common problems (1 pg.) |  | 2018-10-22 | 2018-10-22 | 1
| Customer support (1 pg.) |  | 2018-10-23 | 2018-10-23 | 1
| Edit content. | Proofreader/Editor I | 2018-10-18 | 2018-10-23 | 2
| Test content. | QA Team Member | 2018-10-23 | 2018-10-23 | 1
| g) Illustrations (Print/Online - 45 illus.) |  | 2018-09-10 | 2018-10-19 | 17
| Create illustrations for print and online deliverables. (23 illus.) | Graphic Designer I, II | 2018-09-10 | 2018-09-19 | 8
| Create illustrations for tutorial videos. (22 illus.) | Graphic Designer I, II | 2018-10-09 | 2018-10-19 | 9 | [79 empty] | M
| d) Video tutorials (Online - 18 vids.) |  | 2018-10-09 | 2018-11-07 | 21.5 | [98 empty] | M
| Create and edit videos (animation, audio, etc.). | Videographer | 2018-10-09 | 2018-11-07 | 21.5
| Storyboard content and assist videographer. | Content Strategist III | 2018-10-09 | 2018-11-07 | 21.5
| Review video. | Proofreader/Editor II | 2018-11-02 | 2018-11-07 | 4
| Test Content. | QA Team Member | 2018-11-06 | 2018-11-07 | 2
| e) User support articles (Online - 10 scrns.) |  | 2018-10-23 | 2018-11-05 | 9.5
| Write content. | Content Strategist I, II | 2018-10-23 | 2018-11-05 | 9.5
| Introduction to Online Banking (2 pgs.) |  | 2018-10-23 | 2018-10-24 | 2
| Personal Banking (2 pgs.) |  | 2018-10-25 | 2018-10-26 | 2
| Personal Loans and Mortgages (2 pgs.) |  | 2018-10-29 | 2018-10-30 | 2
| Investing (2 pgs.) |  | 2018-10-31 | 2018-11-01 | 2
| Account Settings, Cheque Orders, and Customer Support (2 pgs.) |  | 2018-11-02 | 2018-11-05 | 1.5
| Edit content. | Proofreader/Editor I | 2018-11-01 | 2018-11-05 | 3
| Test content. | QA Team Member | 2018-11-02 | 2018-11-05 | 2
| f) FAQ guide (Online - 1 scrn.) |  | 2018-11-06 | 2018-11-06 | 1
| Import FAQ content from user guide. | Content Strategist III | 2018-11-06 | 2018-11-06 | 1
| Edit content. | Proofreader/Editor I | 2018-11-06 | 2018-11-06 | 1
| Test content. | QA Team Member | 2018-11-06 | 2018-11-06 | 1
| h) Audio recordings of user guide (Accessible - 25 pgs.) | Accessibility Consultant | 2018-10-01 | 2018-10-08 | 5.5
| i) Braille transcription of user guide (Accessible - 12 pgs.) | Accessibility Consultant | 2018-10-09 | 2018-10-12 | 3.5 | [72 empty] | M
4) Produce (Nov. 13/18 – Nov. 30/18)
| Conduct pre-production test. | Project Manager | 2018-11-13 | 2018-11-13 | 1
| Gain approval from stakeholders to publish content. | Project Manager | 2018-11-14 | 2018-11-14 | 1 | [105 empty] | M
| Upload the online deliverables to the website server. | Project Manager | 2018-11-15 | 2018-11-16 | 2
| Contact printing service company to publish the print deliverables. | Project Manager | 2018-11-19 | 2018-11-21 | 3
| Contact accessibility services to publish the accessible deliverables. | Project Manager | 2018-11-22 | 2018-11-26 | 3
| Contact production coordinator to deliver the print and | Project Manager | 2018-11-27 | 2018-11-30 | 4 | [121 empty] | M
accessible deliverables to Great Pacific Credit Union locations.
5) Evaluate (Dec. 10/18 – Dec. 15/18)
| Collect and analyze project data and customer feedback. | Content Strategist I, II, III | 2018-12-10 | 2018-12-12 | 3
| Evaluate the project’s final budget and schedule development. | Project Manager | 2018-12-10 | 2018-12-12 | 3
| Develop a report that summarizes documentation results. | Project Manager | 2018-12-12 | 2018-12-13 | 2
| Meet with team members to discuss the project | Project Manager | 2018-12-14 | 2018-12-14 | 1 | [135 empty] | M
and identify areas for improvement.
Note on B28: Since Project Shore Line is a new product, we will have little to no source materials to facilitate the documentation development process. This will likely result in the need for additional research and consultation with the development team during the initial writing stages. We plan to create the user guide first, which we will also use as source material to reduce the amount of rewriting and research required for the remaining deliverables. The user guide is the most comprehensive print deliverable. It will contain detailed information on all five core topics about online banking.
Note on B38: The large print guide will contain identical content as the user guide. Work for this deliverable will mainly involve configuring print formatting and layout.
Note on B44: The quick-start pamphlet will contain condensed information from the user guide. Work for this deliverable will mainly involve summarizing procedures and formatting content.
Note on B52: Illustration complexity will range from labelled screenshots to graphics used for the animated video tutorials.
Note on B56: The video tutorials will contain identical content as the user guide with slight differences for video dialogue. Work for this deliverable will mainly involve animating and editing graphics.
Note on B62: The user support articles are the most comprehensive online deliverable. It will contain similar content as the user guide with additional links and support for the video tutorials.
Note on B72: The FAQ guide will contain identical content as the user guide’s FAQ page. Work for this deliverable will mainly involve configuring web formatting and layout.
Note on B77: The audio recordings will contain identical content as the user guide and will also involve recording voice over for the video tutorials’ dialogue.
Note on B79: The braille transcription will contain identical content as the user guide. Work for this deliverable will mainly involve verifying accuracy and adherence to Braille reading standards.